## Gantt Chart
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | 2022-01-10 | 2022-01-10 | 0 | 100% | bar: WEEK 1 M
1.1.1 | Project Charter Revisions | 2022-01-10 | 2022-01-10 | 0 | 100%
1.2 | Research | 2022-01-10 | 2022-01-10 | 0 | 100% | bar: WEEK 1 M to WEEK 3 F
1.3 | Projections | 2022-01-10 | 2022-01-10 | 0 | 75% | bar: WEEK 1 M
1.4 | Stakeholders | 2022-01-10 | 2022-01-10 | 0 | 100% | bar: WEEK 1 M
1.5 | Guidelines | 2022-01-10 | 2022-01-10 | 0 | 100% | bar: WEEK 1 M
1.6 | Risk Management | 2022-01-10 | 2022-01-10 | 0 | 100%
|  | 2022-01-10 | 2022-01-10 | 0 | 0%
|  | 2022-01-10 | 2022-01-10 | 0 | 0%
|  | 2022-01-10 | 2022-01-10 | 0 | 0%
|  | 2022-01-10 | 2022-01-10 | 0 | 0%
2 | Project Design
| Schematics and Parts List |  |  |  | 100%
2.1 | Module 1 The System Clock |  |  |  | 100% | bar: WEEK 3 M to WEEK 3 F
2.2 | Module 2 Registers |  |  |  | 100% | bar: WEEK 3 T to WEEK 6 M
2.3 | Module 3 Arithmetic unit (ALU) |  |  |  | 70% | bar: WEEK 6 M to WEEK 6 F
2.4 | Module 4 Random access memory |  |  |  | 70% | bar: WEEK 6 F to WEEK 7 R
2.5 | Module 5 Program counter |  |  |  | 100% | bar: WEEK 7 R to WEEK 8 W
2.6 | Module 6 Output Register |  |  |  | 50% | bar: WEEK 8 W to WEEK 9 T
2.7 | Module 7 The Bus communication |  |  |  | 50% | bar: WEEK 9 T to WEEK 10 M
2.8 | Module 8 CPU control logic |  |  |  | 50% | bar: WEEK 10 M to WEEK 10 F
2.9 | Module 9 power supply |  |  |  | 100%
3 | Project Prototyping
3.1 | Symulations Testing Methodes |  |  | 0 | 50%
3.2 | Bread Boarding |  |  | 0 | 75%
4 | Project Testing
4.1 | Test Documents |  |  | 0 | 0%
5 | Project Finnal Product
4.1 | Insructions Manual |  |  | 0 | 90%
4.2 | Sales Pitch Presentation |  |  | 0 | 80%
Module 9 power supply